## Lamp
QSOFT VIETNAM CORPORATION Add: Nbr8 No3 Dich Vong Urban Areas, Cau Giay Dist, Ha Noi, Viet Nam Tel: 84-43-792 5148 Fax: 84-43-792 5147 Email: contact@qsoftvietnam.com Website: http://www.qsoftvietnam.com
EFFORT BREAKDOWN AND COST ESTIMATION
Project: Tender: Jewilise
Created by: luanpt
Effective: 16-Aug-2016
Validation time: 45 days
Requirement | Mô tả | Estimation |  |  |  | Total Effort
|  | Men | DB | Client | Hours | Man-hours
1. Platform Agent Generate Coupon/Card | - Platform Agent can add/edit/delete Coupon/Card + Voucher Name + Voucher Code/id: auto generate + Voucher for which normal agent (dropdown list) + Quantity of Voucher + Amount of coupon/card per piece + How many coupon/card + Password: auto generate + Description + Start date and end date - Vouchers created for certain normal agent are exclusively used by users of that agent | 1 | 3 | 12 | 15 | 15
2. Coupon/Card list Platform Agent | - card code/ id - system auto generate itself on every single card - password - system auto generate itself on every single card - downline agent name/url - status: active/used/suspend - used by: show member username once been used. | 1 |  | 7 | 7 | 7
3. Account Summary | - Date Process - Downline Agent url - Total Cards / Total active / Total used/ Total suspend (once suspend-amt will not calculated in the system) - Amount - Pay - Balance |  |  | 10 | 0
4. Downline Agent | Once assigned by the upline: downline system will show at card page: - code/id - amountDo - status - used by |  |  | 7 | 0
5. Downline Agent Account Summary | Account summary will show - Date Process - Total Cards / Total active / Total used/ Total suspend (once suspend-amt will not calculated in the system) - Amount - Pay - Balance ***If happen to be more downline wanted to used. The only one can generate is the Platform agent only. |  |  | 11 | 0
6. Member | Member: - Received code and password - Deposit page select CARD payment - Enter CARd code/id - Enter Card password - (optional) select transfer to which game - system complete. it will show at main wallet. - if transfer to game accept. main wallet will be deducted |  |  | 12 | 0
TOTAL TECHNICAL DEVELOPMENT EFFORT |  |  |  |  | 22 | 22
System Testing & Integration Effort | [5 empty] | 5.5
Project Management Effort | [5 empty] | 5.5
PROJECT TOTAL EFFORT ESTIMATION | [5 empty] | 33
TECHNICAL SELECTION
Programming language: PHP Framework: Laravel and Angular JS
RESOURCE
1 Scrum Master 1 Product Owner 1 Designer 2 Developers
CONSTRAINT/ASSUMPTION
* Responsive Website running on: * PC :Firefox latest version , Chrome latest version, Safari latest version, IE 9 + * iOS: iPhone 4x, 5x, 6.x, iPad 2, 3, 4, Air, iPad mini 1, 2 (iOS 6.x, 7.x, 8.x); (Chrome & Safari latest version) * Android: Phone: 480 x 800, 1280 x 720, 1080 x 1920 ; Android tablet: 1280 x 800, 1024 x 600, 1920 x 1080, 2560 x 1600; Operation System: Android 4.x (Chrome & Android Default Browser latest version)